For phase 1 Lawrence to do all the web work if I am the sole developer.. another developer or two would be good  
A Symbian developer would be able to put together the device application in 3 months with a final month of testing (2 symbian devs would be best)   
Graphics design would be a month lead time be an external design house  
This would be a combination of a flash or silverlight developer and a symbian programmer  
  
**Phase 1**   
  
Symbian software application framework - **2 Months**  
Bluetooth matching + protocol - **1 months, 1 Month further optimisation and configuring**   
*Web site lead web graphic interface design time -* ***1 Month***  
Front end web site including signup, profiles, matches, Top videos and photos and rating system.- **1 Month initial build, ongoing testing, tweaking and optimising 2 months**   
Back end Admin and CMS  - **2 months, 1 month testing**  
Photo Upload from browser - **3 Months, 1 month testing**  
Photo Edit using flash - **3 months, 1 month testing**  
  
**Phase 2**  
  
Bluetooth matching game(s) (including prototyping) - **2 Months, 1 month**  
Bluetooth match scripting - **3 Months, 1 testing**  
Random user marketing and Business user marketing **- 4 Months for public release beta**  
Back end customer managent System, billing and payment system - **2 Months initial Build, 1 Month, 0.5 months external security auditing, 0.5 Security fixing**  
[There may be further delay for the above item if the software has to be certified by banking or payment authorities]  
  
**Phase 3**  
  
DirectX photo rendering 2 Months   
Real time Video streaming from device -  **1 month prototyping, 1 month 2nd phase build months, 2 months final tesing and deployment**  
Real timer video server software - **2 Months, 1 month optimising, 1 month testing**  
Real time Channel switching flash swf - **2 Months, 1 month optimising and testing**  
Bluetooth camera scripting extention - **1 Month, 1 month testing**